## Project Overview
Interactive Social Engineering Training & Evaluation Platform
Planned 30-Day Implementation Roadmap ¦ Client Reference Document ¦ Issued 4 September 2026
PROJECT SUMMARY
Item | Detail
Project name | Interactive Social Engineering Scenario & UI Platform
Project type | Offline training-cum-evaluation application for military personnel
Purpose | Measure and develop judgement against social engineering, using realistic multi-stage simulations rather than multiple-choice testing
Governing specification | Interactive Social Engineering Scenario & UI Development Specification, Version 1.0, 02 September 2026
Planned duration | 30 days (planned delivery roadmap)
Current status | Architecture alignment complete; data foundation next
Simulated platforms | WhatsApp, Instagram, Email, SMS - four contained simulations
Scenario library | 100 client-supplied scenarios (25 per platform)
Scenario structure | Six-stage lifecycle: Notify, Open, Inspect, Branch, Verify, Resolve
Assessment format | 10 scenarios per attempt, scored 0-100
Scoring model | Event-based scoring across the full decision path
Operating mode | Offline-first; no internet dependency at any point
Deployment | Single controlled Windows installation; all data held locally
CURRENT BASELINE - FOUNDATION ALREADY DELIVERED
The programme does not begin from zero. The components below are already built and operational. Where the current specification supersedes earlier assumptions, they are carried forward through alignment and refactoring rather than rebuilt.
Delivered Component | Current State | Roadmap Treatment
Application foundation & design system | Operational | Retained
Learner login & session handling | Operational | Extended for the specified identity contract
Briefing screen | Operational | Extended with versioned acknowledgement
Dashboard foundation | Operational | Redeveloped as a notification-driven orchestrator
Assessment shell & simulation frame | Operational | Refactored to the six-stage lifecycle
WhatsApp / Instagram / Email / SMS renderers | Operational | Refactored onto shared simulation primitives
Scenario data pipeline & validation | Operational | Rebuilt for the specified scenario structure
Attempt lifecycle & API integration | Operational | Extended with event ledger and recovery
Learner attempt history | Operational | Extended with scoring and progress comparison
Administrator authentication foundation | Operational | Retained; administrative features build on it
KEY DELIVERY OBJECTIVES
# | Objective | Measure of Success
1 | Integrate the complete client-supplied scenario library | 100 active scenarios, 25 per platform, each with six stages, scoring and feedback
2 | Deliver realistic, interactive multi-stage simulations | Every scenario produces at least six ordered interaction events
3 | Measure judgement across the whole decision path | Inspection, verification, response and reporting all scored, not only the final answer
4 | Produce an explainable score out of 100 | Scoring reproducible from the recorded decision path
5 | Guarantee reliable persistence and recovery | Closing and reopening resumes at the last committed state with no duplicated scoring
6 | Operate entirely offline | Full operation with networking disabled and no outbound network activity
7 | Maintain a strict simulation boundary | No real credentials, payments, calls, files or external links at any point
8 | Meet accessibility standards | Keyboard-only completion, visible focus, readable contrast, 200% zoom
9 | Provide instructor reporting and oversight | Attempt review, behaviour breakdown and local export
10 | Deliver a supportable installation | Documented install, backup and handover for a controlled offline environment

## 30-Day Roadmap
Planned 30-Day Implementation Roadmap
Sequenced delivery plan. Items marked 'Scope Confirmation Required' await commercial agreement before scheduling.
Day | Phase | Workstream | Planned Activity | Expected Outcome | Dependency | Status | Client Visibility
Baseline | Completed Before Current Roadmap | Application Foundation | Application framework, design system and shared interface components | Reusable foundation available to all later work | - | Completed | Demonstrable
Baseline | Completed Before Current Roadmap | Learner Journey | Login, briefing, dashboard, assessment shell and attempt history | End-to-end learner journey operating | - | Completed | Demonstrable
Baseline | Completed Before Current Roadmap | Platform Simulations | WhatsApp, Instagram, Email and SMS presentation layers | Four platform simulations rendering scenario content | - | Completed | Demonstrable
Baseline | Completed Before Current Roadmap | Platform Services | Scenario pipeline, attempt lifecycle, administrator authentication | Server foundation operating | - | Completed | Internal
1 | Phase 0 | Architecture Alignment | Specification review against the delivered baseline; gap and conflict analysis | Documented alignment position covering every specification area | Specification | Completed | Report
1 | Phase 0 | Classification Design | Attack-family and psychological-trigger classification models for scenario selection and reporting | Deterministic, auditable selection and reporting dimensions | Alignment analysis | Completed | Report
2 | Phase 0 | Platform Architecture | Deployment topology, persistence and recovery strategy for offline operation | Reliable transactional persistence approach confirmed | Alignment analysis | Completed | Report
2 | Phase 0 | Baseline Control | Freeze the architecture baseline and confirm the implementation sequence | Approved plan of record for the delivery phases | Architecture decisions | In Progress | Report
3 | Phase 1 | Environment | Prepare the local database environment for transactional persistence and backup | Environment validated for reliable persistence | Phase 0 | Planned | Internal
3 | Phase 1 | Data Architecture | Scenario definition structure covering identity, classification, six stages, scoring and feedback | Structure able to hold the client scenario library without loss | Phase 0 | Planned | Internal
4 | Phase 1 | Data Architecture | Learner profile, attempt, scenario-run, event and progress record structures | Complete data foundation for assessment and reporting | Scenario structure | Planned | Internal
4 | Phase 1 | Classification | Apply the attack-family and trigger classification models across the scenario library | Every scenario classified for selection and reporting | Data architecture | Planned | Internal
5 | Phase 1 | Content Integration | Validation and import pipeline with six-stage, asset and safety checks | Scenario content validated automatically before publication | Data architecture | Planned | Internal
5 | Phase 1 | Content Integration | Reference scenarios integrated end to end to prove the structure | Structure confirmed against real client content | Import pipeline | Planned | Demonstrable
6 | Phase 1 | Quality Assurance | Automated validation and integrity tests for the data foundation | Data foundation verified | Import pipeline | Planned | Report
7 | Phase 2 | Scenario Engine | Event ledger with ordered, uniquely identified interaction records | Complete decision path captured for every scenario | Phase 1 | Planned | Internal
7 | Phase 2 | Scenario Engine | Duplicate-protection and retry safety across the interaction path | No duplicated scoring or events under interruption | Event ledger | Planned | Internal
8 | Phase 2 | Scenario Engine | Server-controlled six-stage scenario lifecycle with validated transitions | Notify, Open, Inspect, Branch, Verify and Resolve operating under server control | Event ledger | Planned | Demonstrable
9 | Phase 2 | Scenario Engine | Scenario run interfaces for interaction, progress and resolution | Simulation interface able to drive a full scenario | Lifecycle engine | Planned | Internal
9 | Phase 2 | Reliability | Transactional persistence and recovery, including resume after interruption | Attempt state preserved and resumable at the last committed point | Lifecycle engine | Planned | Demonstrable
10 | Phase 2 | Scoring | Event-based scoring with per-scenario limits and 0-100 attempt totals | Explainable score reproducible from the decision path | Lifecycle engine | Planned | Report
11 | Phase 3 | Simulation Framework | Simulation shell, persistent training indicator and stage progress display | Consistent, clearly identified training environment | Phase 2 | Planned | Demonstrable
11 | Phase 3 | Simulation Framework | Notification tray, alerts and interaction dispatch | Scenarios delivered as timed notifications | Simulation shell | Planned | Demonstrable
12 | Phase 3 | Simulation Framework | Contained browser, document viewer and QR inspection components | Link, file and code inspection available and fully contained | Simulation shell | Planned | Demonstrable
13 | Phase 3 | Simulation Framework | Call and voice interaction component with contained response options | Voice-based scenarios supported without any real call capability | Simulation shell | Planned | Demonstrable
13 | Phase 3 | Verification Tools | Trusted directory, action sheet and independent verification source selection | Learners can verify through a known, independent route | Simulation shell | Planned | Demonstrable
14 | Phase 3 | Simulation Framework | Rationale capture, local clock, sound and connection status indicators | Shared simulation layer complete | Simulation shell | Planned | Demonstrable
15 | Phase 4 | Platform Experience | WhatsApp experience refactored onto the shared simulation layer | Conversation, contact, media, link and call interactions available | Phase 3 | Planned | Demonstrable
16 | Phase 4 | Platform Experience | Instagram experience refactored onto the shared simulation layer | Feed, profile, direct message and verification interactions available | Phase 3 | Planned | Demonstrable
17 | Phase 4 | Platform Experience | Email experience refactored onto the shared simulation layer | Inbox, sender detail, link and attachment interactions available | Phase 3 | Planned | Demonstrable
18 | Phase 4 | Platform Experience | SMS experience refactored onto the shared simulation layer | Message thread, sender detail, link and callback interactions available | Phase 3 | Planned | Demonstrable
18 | Phase 4 | Containment | Confirm every platform interaction remains local and inert | No interaction can leave the contained environment | Platform experiences | Validation | Report
19 | Phase 5 | Attempt Orchestration | Notification-driven dashboard with application tiles, unread indicators and status | Dashboard operating as the simulation hub | Phase 4 | Planned | Demonstrable
19 | Phase 5 | Attempt Orchestration | Scenario sequencing, resume handling and interruption recovery | Attempts continue correctly after interruption | Dashboard | Planned | Demonstrable
20 | Phase 5 | Selection Engine | Reproducible selection with recorded selection reference | Attempt composition auditable and repeatable | Phase 2 | Planned | Report
20 | Phase 5 | Selection Engine | Platform rotation, difficulty balance and malicious/legitimate composition | Every attempt meets the specified composition rules | Selection engine | Planned | Report
21 | Phase 5 | Selection Engine | Attack-family and trigger variety, military-context balance and recent-scenario exclusion | Balanced, non-repetitive attempts across repeated use | Selection engine | Planned | Report
21 | Phase 5 | Attempt Orchestration | Results gateway on attempt completion | Attempt preserved before results are presented | Selection engine | Planned | Demonstrable
22 | Phase 6 | Results & Feedback | Results aggregation with platform, attack-family, trigger and action-stage breakdown | Clear picture of where judgement succeeded or failed | Phase 5 | Planned | Demonstrable
22 | Phase 6 | Results & Feedback | Decision-path replay and per-scenario feedback | Learner can see what they did and what to do differently | Results aggregation | Planned | Demonstrable
23 | Phase 6 | Results & Feedback | Targeted remediation recommendations and progress comparison across attempts | Measurable development over repeated attempts | Results aggregation | Planned | Demonstrable
23 | Phase 6 | Learner History | Attempt history extended with scores, trend and exposure | Complete local record of learner progress | Results aggregation | Planned | Demonstrable
24 | Phase 6 | Instructor Tools | Attempt review by learner and date, with decision path and remediation | Instructors can review performance without exposing sensitive content | Results aggregation | Scope Confirmation Required | Demonstrable
24 | Phase 6 | Instructor Tools | Scenario management, reset and archive workflows with change logging | Controlled scenario administration with an auditable change record | Phase 1 | Scope Confirmation Required | Demonstrable
24 | Phase 6 | Reporting | Local export of attempt and summary reporting | Offline reporting available to instructors | Attempt review | Scope Confirmation Required | Report
25 | Phase 7 | Security & Containment | Enforced network boundary and content security controls | Outbound activity prevented by design, not by absence | Phase 5 | Planned | Report
25 | Phase 7 | Security & Containment | Confirm no real credential, payment, dialling, camera or external-link capability exists | Simulation boundary verified across all 100 scenarios | Phase 4 | Validation | Report
26 | Phase 7 | Offline Verification | Full operation verified with networking disabled | Every scenario, asset, report and feedback path works offline | Security controls | Validation | Report
26 | Phase 7 | Privacy | Review of stored fields, logging and export content | Only permitted information retained; records remain local | Phase 1 | Validation | Report
27 | Phase 7 | Accessibility | Keyboard-only operation, focus visibility, contrast, zoom and non-colour indicators | Accessibility criteria met across the application | Phase 4 | Planned | Report
28 | Phase 8 | Content Validation | Validate and integrate the complete client-supplied 100-scenario library | 100 active scenarios, 25 per platform, fully playable | Phase 4 | Planned | Demonstrable
28 | Phase 8 | Content Validation | Confirm every scenario is completable along its safe path | No scenario blocks a correctly behaving learner | Content integration | Validation | Report
29 | Phase 8 | Acceptance Testing | Selection, scoring, state-recovery and duplicate-protection test suites | Specified behaviour demonstrated by automated tests | Phase 5 | Validation | Report
29 | Phase 8 | Acceptance Testing | Full regression across the learner journey and all four platforms | No regression in delivered functionality | All phases | Validation | Report
30 | Phase 8 | Release Preparation | Installation package, environment setup and backup procedure | Repeatable installation for the controlled environment | All phases | Planned | Demonstrable
30 | Phase 8 | Client Handover | Handover documentation, administrator guidance and release candidate | Release candidate accepted and handed over | Release preparation | Planned | Demonstrable

## Milestones
Delivery Milestones
Ten checkpoints across the planned roadmap, each with a defined acceptance condition.
Milestone | Target Day | Milestone Name | Deliverable | Acceptance Condition
M1 | 2 | Architecture Baseline | Approved architecture and implementation plan of record | Alignment position, classification models and persistence strategy documented and approved
M2 | 6 | Data Foundation Ready | Scenario, learner, attempt and event data structures with validated import pipeline | Reference scenarios import, validate and reproduce without loss of client content
M3 | 10 | Scenario Engine Ready | Six-stage lifecycle, event ledger, recovery and event-based scoring | A scenario runs end to end under server control; interruption and retry produce no duplicate scoring
M4 | 14 | Shared Simulation Layer Ready | Simulation shell, notifications, browser, file, code, call and verification components | Each component demonstrable in isolation and fully contained
M5 | 18 | Platform Experiences Ready | WhatsApp, Instagram, Email and SMS experiences on the shared layer | All four platforms deliver their specified interaction surfaces; all interactions remain local
M6 | 21 | Attempt Orchestration Ready | Notification-driven dashboard and reproducible selection engine | Generated attempts meet every composition rule; interrupted attempts resume correctly
M7 | 24 | Results & Instructor Tools Ready | Results, feedback, remediation, history and instructor review | Behaviour breakdown and decision-path replay produced from recorded activity
M8 | 27 | Security, Offline & Accessibility Validated | Network boundary, containment, privacy and accessibility verification | Full operation with networking disabled and no outbound activity; accessibility criteria met
M9 | 29 | Full Scenario Library Validated | Complete 100-scenario library integrated and tested | 100 active scenarios, 25 per platform, each completable with correct scoring
M10 | 30 | Release Candidate & Client Handover | Installable release candidate with handover documentation | Installation reproducible in the target environment; acceptance checklist satisfied

## Scope & Deliverables
Scope & Deliverables
Delivery scope by area. Items awaiting commercial agreement are marked 'Scope Confirmation Required'.
Area | Deliverable | Description | Status | Planned Phase | Notes
Learner Journey | Identification & briefing | Learner identification with masked service number, versioned briefing acknowledgement and local progress record | Enhancement | Phase 1 | Extends the delivered login and briefing screens
Learner Journey | Attempt lifecycle | Start, resume and complete a 10-scenario attempt with reliable state recovery | Enhancement | Phase 2 | Extends the delivered assessment shell
Dashboard | Simulation hub | Persistent training indicator, local clock, connection status, learner chip and attempt progress | Redevelopment | Phase 5 | Supersedes the delivered dashboard layout
Dashboard | Notification orchestration | Timed scenario notifications, alert tray, application tiles and unread indicators | New | Phase 5 | Core to the specified experience
WhatsApp | Conversation experience | Chat list and thread, contact detail, media and attachments, links, calls and verification actions | Refactor | Phase 4 | Presentation layer already delivered
Instagram | Social experience | Feed, profile, posts, direct messages, verification indicators and support patterns | Refactor | Phase 4 | Presentation layer already delivered
Email | Mailbox experience | Inbox and reading view, sender detail, links, attachments and verification routes | Refactor | Phase 4 | Presentation layer already delivered
SMS | Messaging experience | Message list and thread, sender detail, links, callback handling and verification | Refactor | Phase 4 | Presentation layer already delivered
Shared Simulation | Simulation framework | Simulation shell, notifications, stage progress and interaction dispatch | New | Phase 3 | Shared across all four platforms
Shared Simulation | Inspection components | Contained browser, document viewer and code inspection | New | Phase 3 | All content local and inert
Shared Simulation | Call & verification components | Call and voice screen, trusted directory, action sheet, verification source selection and rationale capture | New | Phase 3 | Supports independent verification behaviour
Scenario Engine | Six-stage lifecycle | Server-controlled Notify, Open, Inspect, Branch, Verify and Resolve progression | New | Phase 2 | Replaces the single-response assessment model
Scenario Engine | Interaction ledger | Ordered, uniquely identified record of every interaction with duplicate protection | New | Phase 2 | Basis of scoring and decision-path replay
Selection Engine | Attempt composition | Platform rotation, difficulty balance, malicious/legitimate mix, variety rules and recent-scenario exclusion | Redevelopment | Phase 5 | Supersedes the earlier selection approach
Selection Engine | Reproducible selection | Recorded selection reference allowing an attempt to be reproduced for audit | New | Phase 5 | Supports assurance and review
Scoring | Event-based scoring | Scoring across the decision path with per-scenario limits and a 0-100 attempt total | New | Phase 2 | Replaces the earlier per-answer model
Results | Behaviour breakdown | Platform, attack-family, trigger and action-stage results distinguishing missed threats from false alarms | New | Phase 6 | Specified reporting output
Results | Feedback & remediation | Per-scenario feedback, decision-path replay and targeted practice recommendations | New | Phase 6 | Blame-free instructional language
History | Progress comparison | Attempt history with score, trend and exposure count across comparable attempts | Enhancement | Phase 6 | Extends the delivered history feature
Administration | Attempt review | Review attempts by learner and date with decision path and remediation | Scope Confirmation Required | Phase 6 | Extends the delivered administrator authentication
Administration | Scenario management | Create, edit, clone, deactivate and version scenarios with validation before publication | Scope Confirmation Required | Phase 6 | Expands the originally agreed administrative scope
Administration | Controls & change log | Attempt reset, profile archive, feedback timing configuration and an append-only change log | Scope Confirmation Required | Phase 6 | Expands the originally agreed administrative scope
Reporting | Local export | Offline export of attempt and summary reporting to an instructor-selected local location | Scope Confirmation Required | Phase 6 | Export format to be confirmed
Offline & Safety | Containment boundary | Enforced network boundary with all browser, file, code, call and payment experiences local and inert | New | Phase 7 | Verified with networking disabled
Offline & Safety | Privacy controls | Restricted stored fields, controlled logging and local-only records | New | Phase 7 | No real credentials, payment or biometric data at any point
Accessibility | Accessibility compliance | Keyboard-only operation, visible focus, readable contrast, 200% zoom and non-colour indicators | New | Phase 7 | Verified during acceptance
Content | Scenario library integration | Validate, transform and integrate the client-supplied 100-scenario library into the delivery structure | New | Phase 8 | Client-supplied content; not authored by the delivery team
Handover | Installation & documentation | Installation package, environment setup, backup procedure and handover documentation | New | Phase 8 | For the controlled offline environment

## Dependencies & Risks
Dependencies & Risks
Active delivery risks and dependencies with planned mitigation.
Risk / Dependency | Impact | Mitigation | Planned Resolution | Status
Administrative scope confirmation | The specification requires broader administrative capability than originally agreed, including scenario management and change logging | Administrative items are planned and costed but held pending commercial agreement; all other phases proceed independently | Phase 6 | Open - Client Decision
Scenario library integration effort | The client library comprises 100 scenarios across 600 interaction stages and is the largest single work item | Structure proven against reference scenarios first, then integrated in platform batches with automated validation and content review | Phases 1 and 8 | Managed
Shared component sequencing | Building simulation components separately for each platform would create avoidable rework | The shared simulation layer is completed before platform work begins | Phase 3 | Managed
Reliable persistence under interruption | Interruption during a scenario could otherwise cause duplicated scoring or lost progress | Transactional persistence with duplicate protection and verified resume behaviour | Phase 2 | Resolved - Design Approved
Deployment environment configuration | Reliable persistence requires a specific local database configuration | Configuration defined and included in the installation procedure and handover documentation | Phases 1 and 8 | Resolved - Design Approved
Enforced offline boundary | Offline operation must be enforced by design rather than achieved by absence of functionality | Explicit network controls plus verification with networking disabled and outbound monitoring | Phase 7 | Planned
Data resilience in a single-machine installation | A single local installation holds the only copy of training records | Documented backup and restore procedure provided as part of handover | Phase 8 | Planned
Classification model ownership | Scenario selection variety and reporting depend on classification models developed for delivery | Models documented, versioned and auditable; client content preserved unchanged and models replaceable if required | Completed in Phase 0 | Resolved
Accessibility verification timing | Accessibility assessed against interim interfaces would need repeating | Formal accessibility verification scheduled after the interface work completes | Phase 7 | Managed
Scenario content clarification | Isolated content questions may arise during integration | Questions logged and raised in batches; client content is never altered unilaterally | Phases 1 and 8 | Monitored

## Acceptance Checklist
Acceptance Checklist
Acceptance criteria derived from the governing specification. Status reflects verification actually performed.
Category | Acceptance Item | Planned Validation | Status
Scenario Coverage | 100 active scenarios, 25 per simulated platform | Automated content validation | Not Yet Verified
Scenario Coverage | Each scenario carries six stages, scoring, end state and feedback | Automated content validation | Not Yet Verified
Scenario Coverage | Library composition matches the specified difficulty and disposition mix | Automated content validation | Not Yet Verified
Six-Stage Interaction | Every scenario produces at least six ordered interaction events | Engine test suite | Not Yet Verified
Six-Stage Interaction | Only valid stage transitions are accepted | Engine test suite | Not Yet Verified
Six-Stage Interaction | Unsafe and safe controls are both interactive and scored | Scenario walkthrough | Not Yet Verified
Scoring | Each recorded action scores exactly as specified | Automated scoring tests | Not Yet Verified
Scoring | Per-scenario score limits and 0-100 attempt totals applied correctly | Automated scoring tests | Not Yet Verified
Scoring | All critical unsafe actions and false-alarm penalties covered by tests | Automated scoring tests | Not Yet Verified
Scoring | Score reproducible from the recorded decision path | Replay verification | Not Yet Verified
Attempt Composition | Exactly 10 scenarios per attempt | Selection test suite | Not Yet Verified
Attempt Composition | Specified malicious and legitimate mix, drawn from different platforms | Selection test suite | Not Yet Verified
Attempt Composition | Specified difficulty balance and platform rotation | Selection test suite | Not Yet Verified
Attempt Composition | Variety rules and recent-scenario exclusion applied | Selection test suite | Not Yet Verified
Attempt Composition | Attempt composition reproducible from its recorded reference | Selection test suite | Not Yet Verified
Offline Operation | All scenarios, assets, reports and feedback work with networking disabled | Offline verification | Not Yet Verified
Offline Operation | No outbound network activity observed during a full attempt | Network monitoring | Not Yet Verified
Safety & Containment | No real credential, one-time code, payment or biometric entry exists | Security review | Not Yet Verified
Safety & Containment | No real dialling, camera, clipboard or external link capability | Security review | Not Yet Verified
Safety & Containment | Files, codes and pages are inert and cannot act on the host system | Security review | Not Yet Verified
Safety & Containment | Verification sources cannot be populated from suspect message content | Scenario walkthrough | Not Yet Verified
Recovery | Closing and reopening resumes at the last committed state | Recovery test suite | Not Yet Verified
Recovery | No duplicated scoring or events after interruption or retry | Recovery test suite | Not Yet Verified
Recovery | Attempt preserved before results are presented | Recovery test suite | Not Yet Verified
Accessibility | A full attempt completable using the keyboard alone | Accessibility assessment | Not Yet Verified
Accessibility | Visible focus, readable contrast and clear labelling throughout | Accessibility assessment | Not Yet Verified
Accessibility | Usable at 200% zoom with no meaning conveyed by colour alone | Accessibility assessment | Not Yet Verified
Privacy | Only permitted learner information is stored | Privacy review | Not Yet Verified
Privacy | Activity logging restricted to approved information | Privacy review | Not Yet Verified
Privacy | Records remain on the local system; exports are explicit and local | Privacy review | Not Yet Verified
Results | Score presented with per-scenario detail | Results verification | Not Yet Verified
Results | Breakdown distinguishes missed threats from false alarms | Results verification | Not Yet Verified
Results | Decision-path replay contains no sensitive entered content | Results verification | Not Yet Verified
Results | Progress comparison only between comparable attempts | Results verification | Not Yet Verified
Reporting | Instructor attempt review available | Instructor walkthrough | Scope Confirmation Required
Reporting | Local export produced and clearly marked as training data | Instructor walkthrough | Scope Confirmation Required
Reporting | Administrative changes recorded in an append-only log | Instructor walkthrough | Scope Confirmation Required
Release Readiness | Interface state remains consistent under interruption and retry | Regression testing | Not Yet Verified
Release Readiness | Installation reproducible in the target environment | Installation verification | Not Yet Verified
Release Readiness | Backup and restore procedure verified | Installation verification | Not Yet Verified
Release Readiness | Handover documentation complete and accepted | Client handover | Not Yet Verified
Note: acceptance status is recorded only after verification has actually been carried out. No item is marked as satisfied in advance of testing.

## Timeline Summary
Timeline Summary
Planned 30-day delivery schedule by workstream.
Phase | Workstream | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Phase 0 | Alignment & Architecture | bar: 1 to 2
Phase 1 | Data Foundation | bar: 3 to 6
Phase 2 | Scenario Engine & Scoring | bar: 7 to 10
Phase 3 | Shared Simulation Layer | bar: 11 to 14
Phase 4 | Platform Experiences | bar: 15 to 18
Phase 5 | Attempt Orchestration | bar: 19 to 21
Phase 6 | Results, History & Instructor Tools | bar: 22 to 24
Phase 7 | Security, Offline & Accessibility | bar: 25 to 27
Phase 8 | Validation & Release | bar: 28 to 30
| Milestones | 2: M1; 6: M2; 10: M3; 14: M4; 18: M5; 21: M6; 24: M7; 27: M8; 29: M9; 30: M10
Bars indicate the planned working window for each workstream. Milestone markers show the day each checkpoint is planned to be reached.